Priscilla & Robert Wheeler

46 Daniels Road

675-9126

Permit # 2012-53

Map/ID # 107/37

1097 Route 12A

Renovation, move 10’, foundation, 24x30 addition

10-08-12	Permit 2012-53, 1097 Route 12A. Priscilla called to let me know that Wednesday or Thursday that the footer forms will be ready for inspection. I stopped by and talked to the contractor and let him know what I needed to see when they were ready to pour.

Time 0.4

10-12-12	Permit 2012-53, 1097 Route 12A. Looked at footer forms with rebar installed and ground wire. Looked okay and they will pour on Monday.

Time 0.3

10-24-12	Permit 2012-53, 1097 Route 12A. I inspected the wall forms and they were okay. They had to raise the house to get the wall forms up. That is why I haven’t seen them up on my way by.

Time 0.3

01-08-13	Permit 2012-53, 1097 Route 12A. I received an email with pictures of the perimeter drains around the main foundation. Looked okay and I told them they could backfill.

Time 0.2

01-15-13	Permit 2012-53, 1097 Route 12A. I received an email with pictures for the footer forms for the rear addition. Looked okay and I told them they could pour when they were ready and the weather cooperated.

Time 0.2

01-24-13	Permit 2012-53, 1097 Route 12A. I received an email with pictures showing the wall forms for the rear addition. Looked okay and let them know they could pour.

Time 0.2

02-15-13	Permit 2012-53, 1097 Route 12A. I received an email including pictures of the rough in plumbing for a future bathroom in the basement including the pump tank. I let them know that they could cover.

Time 0.2

05-04-13	Permit 2012-53, 1097 Route 12A. I noticed they were back from vacation and when I talked to them earlier about egress windows they said they would begin working on the house again. I inspected the basement, had some water in the addition, the beams and support posts looked okay. Where they put the new stairs along the back wall of the original house, a 2x4 wall was constructed parallel to the stairs that supported the cut off beams from the front wall. I told her that that wall needed to have more support for the beams. One of the beams over the bathroom had a large piece cut out and had a block of wood inserted and a 3-4 foot 2x6 nailed to each side. I will have to look to see what load is on that beam as there is a second floor above it but no send floor wall. the ceiling of the left upstairs room is the inside of the roof that they had installed rafters over the roof, insulated with four inches of foiled foam insulation that should have an R-factor of between 28 and 32. For an roof with no attic you need R-30 instead of R-49. We talked about wall insulation and R-values. I would research when I got home as well as stair requirements. Riser should be no more than 7-3/4’s and tread no less than 10 inches. Also all steps must be the same size. They will call when the electrical trench is ready for inspection. It looks like a commercial kitchen in the addition and a two or three bedroom, two bath in the front part of the building with a large open area. No detail as to if there is a kitchen in the main part. Not sure what is going to be upstairs of the new addition. I will need more detail.

Time 0.7 and 0.7 for codes.

07-01-13	Permit 2012-53, 1097 Route 12A. Met with Robert, Priscilla and Steve to look over the framing as I was concerned about the strength of the old beams. I wanted the beams inspected by an expert to see if they would  support the weight of the second floor. When we got there Robert had replaced some of the old beams and had plans to replace all the old beams with new ones. I felt comfortable with the new beams and let Steve know along with Robert.

Time 0.9

07-25-13	Permit 2012-53, 1097 Route 12A. Johanna asked me to inspect the trench and meter panel installation. Wasn’t ready, I will go back later.

Time 0.5

07-25-13	Permit 2012-53, 1097 Route 12A. I inspected the trench with conduit and told them they could backfill. Johanna still needs to mount circuit panel and feed from meter to panel. PSNH will run electrical wires from the pole to the meter panel.

Time 0.4

08-07-13	Permit 2012-53, 1097 Route 12A. I saw that the deck was almost completed and wanted to inspect the fasting of the ledger boards and to see if joist hangers were used as well as hurricane straps or other tie down brackets. A section of the handicap ramp needed straps and I left a note.

Time 0.2

08-08-13	Permit 2012-53, 1097 Route 12A. I stopped by as the contractor was there. He saw my note and said he ran out of brackets/hangers. They were installed today and looked okay. He wanted my opinion about the beams and the plan for the second floor as Wheelers wanted to place 2x6's on their side on top of the beams and then plywood flooring. The beams were anywhere from two to four feet apart and their length was about seventeen feet. Span of beams too far for 6x6's without additional support and 2x6 joists on their side for a span of four feet would be too far. A person on the 6x6 just walking caused it to bounce. He was concerned about that and I told him it needed a center support for the beams and the 2x6's would have to be on their edge. He would talk to Robert. The contractor appears to do very good work and is very conscientious.

Time 0.4

08-12-13	Permit 2012-53, 1097 Route 12A. Stopped by as Pricilla was there with the contractor. They are going to put manufactured beams along the 6x6's and in between where the gap is two big. He is also going to install ledger boards under the ends of the beams as some of them were notched more that 20%. That solution should support the second floor load.

Time 0.2

10-15-13	Permit 2012-53, 1097 Route 12A. Contractors were there and I stopped in to see progress. The manufactured beams were installed as per my conversation on 8/12. The tongue and groove flooring was installed on the second floor and then OSB sheathing. No bounce. In the basement they installed several 8x8 posts supporting large beams down the center of the original house supporting the first floor joists. New 2x6 rafters were installed on the right half of the house. New studs were being installed on the right front wall on the second floor. Looked good.

Time 0.2

David H Lersch

Plainfield Building Inspector