Eric Berry

88 Methodist Hill Road

727-2664

Permit # 2017-54

Map/Lot 212 15

sfh

08-01-17	Permit 2017-54, 88 Methodist Hill. I inspected the footer forms for the 			house and discussed where and how power will be run (aerial, buried or a 			combination, also where the service entrance will be.) They decided it 			would be in the basement of the house so they installed the ground wire 			there in the footer and sent me a picture after the decision was made.

Time 0.6

08-03-17	Permit 2017-54, 88 Methodist Hill Road. Inspected the wall forms for the 			house. Okay. They were going to try to pour footer for garage if time. Will 		send pictures if ready to pour with wall. Told Justin to send picture and I 			will text if okay to pour. Used key lock (v-grove ) in footer instead of 			vertical rebar. They were planning on pouring the frost wall Monday and I 		told them I would have Brad do the inspection, told them do not pour 			unless it is inspected first.

Time 1.0

08-04-17	Permit 2017-54, 88 Methodist Hill Road. Didn't here from Justin, so I 			went  by to see the forms for the garage footer. Already poured, no vertical 		rebar and I didn't notice the key lock. Footer was not continuous, two short 		sections from house footer to side of basement excavation, at ground level 			was the u shaped footer for the garage, no step to lower footer sections. 			Footer should be continuous with rebar. I will text Justin.

He texted back he sent the pictures and yes he did the key lock. Got 			pictures of footer forms after texting him Friday morning. I texted I will 			stop by later or tomorrow morning.

Time 0.4

08-05-17	Permit 2017.54. 88 Methodist Hill Road. I went to see progress and verify 			key lock, frost wall was already poured without notifying me for an 			inspection. Texted Justin of findings and told him to stop work until I have 		some proof of key lock and pictures of wall forms. Eric called later on 			Saturday asking what was going on. To be brief, Footer should not have 			been poured until I gave the okay, either on site or after reviewing 				pictures. Also frost wall must have been poured on Friday without calling 			me after I had texted Justin earlier. They were told not to pour until getting 		an inspection. So they poured the footer and wall without approval. I 			checked some online codes and footers should be continuous with rebar. I 			called Eric and let him know and he is going to let Justin deal with it.

Time 0.4

08-15-17	Permit 2017-54, 88 Methodist Hill Road. Robbie called and wanted to 			backfill as the perimeter drains were ready for inspection. Looked okay 			and told Robbie he could backfill.

Time 0.2

08-18-17	Permit 2017-54, 88 Methodist Hill Road.  Jason called to have me inspect 			the foam insulation he installed under the garage and house floors before 			he poured them. It was not required but he installed two inches of blue 			foam. We went over the construction of the garage wall and he had 			pictures he showed me and would send them.

Time 0.9

08-29-17	Permit 2017-54, 88 Methodist Hill Road. Jason notified me that the 			temporary power was ready for inspection. I checked it out and to the top 			of the 6x6 was only 11', I think it is usually 12'. After I got home looked at 		Eversource and NH Co-OP, both specified 12'. I went to Liberty site and 			found their Spec. for Elec. Inst. and they specified 14'6". Sent a text to 			Jason, he called and said the Liberty guy said since pole was close 11' 			would be okay. Jason wanted to be sure so he will attach another 6x6 so it 			will meet specifications for Liberty Utilities. I emailed Liberty and gave 			them this information.

Time 1.5

09-26-17	Permit 2017-54, 88 Methodist Hill Road. Stopped in to see progress, all 			framed and setting piers for front deck. Looked okay, still no utility poles 			set yet, so there isn't any electricity.

Time 0.4

11-01-17	Permit 2017-54, 88 Methodist Hill Road. Stopped by on way to Eaton 			Road and inspected some of the rough in electrical and plumbing. They 			finally have power to the pedestal. Most of the siding was installed. 			Should be ready in the next two weeks for the final rough in inspection.

Time 0.8

11-07-17	Permit 2017-54, 88 Methodist Hill Road. Electrician called to have me 			inspect the trench and conduit from the pedestal to the corner of the 			garage. Looked okay. I completed the electrical rough in inspection as 			well.

Time 1.4

11-15-17	Permit 2017-54, 88 Methodist Hill Road. Jason called and scheduled a 			rough in plumbing inspection for today. All the plumbing that is in the 			exterior walls is okay and can be insulation. The sewer pipes in the 			basement still need to be connected. Water lines under 60 pounds of 			pressure. Buried electric from the pole to the rear of the garage still not 			pulled and wires need to be connected to the main panel in the basement. 			Jason scheduled with me for 7AM Monday morning for the insulation 			inspection.

Time 0.5

12-08-17	Permit 2017-54, 88 Methodist Hill Road. Brad inspected the service from 			the pole to the meter panel on the left side of the garage. Electrician said 			Liberty said it was okay at that location, not gable end. Notified Liberty it 			was okay to connect permanent power and remove temporary service.

Time 0.5

- 12-08-17	Permit 2017-54 88 Methodist Hill – New House Service Entrance – for power 				company energize. Met Jeremy (?) on-site. New meter box with disconnect on 				eave edge (power company approved location) Everything looked good. 					Underground to pole.

- 01-05-17         Permit 2017-54, 88 Methodist Hill Road. Met Todd Marsh / Justin Root

on-site @ 9:00am (approx.) for insulation inspection prior to sheetrock

installation. R-21 fiberglass batt insulation installed in exterior walls and

R30 fiberglass plus blown-in cellulose in the roof to total R49.    	                	         Continuous(clear) poly sheet was installed over stud-face. Insulation

behind poly appeared neatly installed with no obvious gaps, voids or

distortions.

Stud / rafter bays completely filled with no apparent gaps at top

or bottom, eave or ridge. Basement below grade concrete wall had 2x4 stud 	      wall with air space behind and R-13 Faced fiberglass. Above grade wall had 	       R21 Fiberglass. Todd indicated that sheetrock would be installed on all

walls & ceiling upstairs and down the stairwell with basement walls and

ceilings to be covered later. I indicated that poly/kraft-faced insulation

would probably need to be covered to receive final co/cc, but

that would be your call. I conveyed this concern to you later Friday when

we spoke on the phone. BRAD

01-26-18		Permit 2017-54, 88 Methodist Hill Road. Justin called and wanted to

know if I issued a CO yet. I said no one called for a final inspection. He

said he has the letter I requested and he said he hasn't been paid yet.

I am not sure if they moved in yet, will ask Brad.

Time 0.2

01-31-18	Permit 2017-54, 88 Methodist Hill Road. Hi Dave, I met with Justin Root 			at 88 Methodist Hill Rd. at noontime today for the final inspection. He 			walked me though the building. There were a few unfinished items,;

Garage side of entry door was uncased and the jamb was not sealed, so I 			think it needs to be fire stopped/foamed and cased.

Garage - There were a number of device cover plates missing (outlets and 			switches). Trim plates need to be installed on all outlets and switches.

Kitchen / Bath – Plumbing; faucets /traps/drains missing, not connected. 			Stub outs 	look fine. This needs to be completed.

No hand rail on stairs to the lower level. Handrail is required. This needs 			to be completed.

Otherwise, what I saw looked fine. Owner appears to be partially moved 			in. I can return when the work is actually finished to complete the 				inspection, or you can accept pictures. Just let me know. Brad

02-13-18	Permit 2017-54, 88 Methodist Hill Road. I spoke w/Justin on the phone 			and he agreed to have the owner leave the door open. I stopped by the site 			and confirmed that the following items have been completed;

Outlet covers were installed on all openings in the garage.

Trim was installed on the garage side of the entry door into the home.

Fixture drains and supplies were connected in the kitchen and bathroom.

A handrail is installed (upper flight only) on the stairway to the lower 			level. The lower flight (4 risers) does not have a handrail. It does have a 			full wall on one side and a half wall with wooden cap on the other side.

The new work is clean and neat. Regards, Brad

02-14-18	Permit 2017-54, 88 Methodist Hill Road. Received Brad's report. Also 			sent text to Justin and Brad as four or more steps (risers) require a hand 			rail. Justin will install one and send me picture. I will issue a CO.

David H Lersch

Plainfield Building Inspector