Kimball Union Academy

PO Box 188

Meriden

469-2152

Permit # 2016-14

Map/Lot 103/4

replace floor, concrete bases for I-beams for additional roof supports

16 Campus center drive

05-18-16	Permit 2016-14, KUA Ice Rink. Inspected the forms for the new roof supports and the footer forms for the well for the Zamboni. Rebar installed and gave them the okay to pour.

Time 0.4

05-23-16	Permit 2016-14, KUA Ice Rink. I inspected the wall forms for the well. Looked okay.

Time 0.6

06-21-16	Permit 2016-14, KUA Ice Rink. Inspected some of the water heating  piping that will go under the foam insulation to keep that area about 40 degrees and the coolant piping to make ice so they could backfill. The rest of the piping will be installed next week.

Time 0.6

06-30-16	Permit 2016-14, KUA Ice Rink. Inspected the drains and piping and the foam insulation for the rink floor. The next inspection will be for the rebar

and the cooling pipes that will be snaked around the ice rink floor prior to pouring the concrete floor.

Time 0.8

07-11-16	Permit 2016-14, KUA Ice Rink. All the rebar was installed and one half of the cooling pipes. They will have the rest completed and the wire installed over the pipes for inspection on the 18th.

Time 0.2

07-18-16	Permit 2016-14, KUA Ice Rink. Inspected the completed installation of the cooling pipes with the pressure test on them. All the wire mesh was installed over the pies and they are ready to pour concrete. All okay.

Time 0.6

David H Lersch

Plainfield Building Inspector