Kimball Union Academy

PO Box 188

Meriden

469-2152

Permit # 2019-27

Map/Lot 103/1

Attached 2 car garage with 2nd floor bedroom

13 Chellis Road

05-31-19	Met with Barden concrete to inspect the footer forms for the 				garage/apartment. Three rows of rebar, supported on chairs, tied 			together, with vertical rebar L's installed and tied to horizontal rebar. 		Ground installed and coil near the left front of the house. I gave the 			okay to pour concrete.                                                                  			Time 0.5

06-04-19	Inspected the wall forms with rebar installed, tied together and bent 			around corners. Looked okay and told them they could order 			concrete.

Time 0.4

07-22-19	Haven't heard from KUA, called Doug, he emailed his people and 			contractors to get in touch with me. Tim from Estes and Gallop			called me and there was some confusion on inspection sheet as it 			didn't have checkmarks. It was a copy of the new inspection sheet I 		gave Doug as a reference. Framing is mostly completed, roof being 		put on, no concrete work since I was there. Foundation wall was 			sealed but never inspected. Two other permits were discussed and 			I will update those notes when I do an inspection.

Time 0.2

07-30-19	Met with contractor and KUA staff to inspect the garage. Garage 			part not heated but had two inches of blue foam and a vapor 				barrier. The floor in the other section had insulation against the 			garage side and three inches of blue foam with vapor barrier. 			Framing looked okay, will call when insulation is installed.

Time 0.4

08-13-19	Mike called to do the rough in inspection of the electrical on the 			second floor. Looked okay, Spraying foam insulation of roof.

Time 0.4

08-20-19	Inspected the rest of the rough in electrical wiring in the garage so 			they could spray insulation. Looked okay and will stop Thursday 			and inspect the insulation.

Time 0.4

08-22-19	I inspected the spray foam insulation in the walls, garage ceiling. 			Looked okay. Under the stairs will be a propane wall mounted 			water heater and I said that that area under the stairs needed to 			have fire rated sheetrock installed.

Time 0.6

10-28-19	Inspected the almost completed garage with bedroom upstairs. 			Upstairs completed, garage completed, needs stair railings 				installed, two holes in garage fire stopped, and under stairs finish 			installing sheetrock. Downstairs bathroom needs tiled and fixtures 			installed.

Time 0.7

11-07-19	Completed the final inspection. Holes fire stopped, downstairs 			bathroom finished, all slate flooring installed, hand railing to 				upstairs installed, and under stairs all sheetrock installed and was 			taped and compound applied. I will issue a CO.

Time 0.4

David H Lersch

Plainfield Building Inspector

Certificate of Occupancy

TOWN OF PLAINFIELD, NH

This certifies that the building owned by Kimball Union Academy at 13 Chellis Road, Meriden, NH may be occupied in accordance with the provisions of the 2015 International Residential Code and the Codes of the Town of Plainfield.

Description of Structure: An attached garage for two vehicles, and entry foyer containing a handicap bathroom and stairs to the spare bedroom/playroom upstairs.

Portion of structure inspected: Completed garage with spare bedroom, a bathroom, and an entry foyer.

Building Permit # 2019-27

Map/Lot:  103-01

Name: 	Kimball Union Academy

Address:  PO Box 188

Meriden, NH 03770

11-07-2019

Building Code Official Signature   Date

David H. Lersch