Diane and Mark Walker

392 Merry Hill Road

Barrington, NH 03825

969-0577

Permit # 2015-52

Map/Lot 105/27

28x44 cape w/two car attached 24x24 garage

15 Baynes Road (lot 9)

09-08-15	Permit none,15 Baynes Road. I received a call from the owner of the lot to have me inspect the temporary service so Liberty Utilities would hook up power. I told her I needed a work order number, but I would go by and inspect the temporary service installation. I went by and some site work was being done but nothing as far as the temporary service. Also I looked over my permits and I don't have one for 9 Baynes.

Time 0.6

10-12-15	Permit 2015-52, 15 Baynes Road. Saw contractor at site when at 12 Baynes. Discussed electrical hookup for temporary. He wants to go all the way to the house location instead of a pedestal. He is going to have to blast as it is ledge from the transformer to the house near the road. He will call when he gets the trench ready or any concrete work.

Time 0.4

12-21-15	Permit 2015-52, 15 Baynes Road. Went by as the work has started up. They were blasting for the trench for the utilities. Answered some question for the contractor regarding insulation of the foundation and floor.

Time 0.4

01-06-16	Permit 2015-52, 15 Baynes Road. I inspected the footer forms, rebar and ground wire and all was okay. Lots of ledge and pins were installed where footer wasn't as thick. He said he would be ready for the wall form inspection late Friday.

Time 0.3

01-08-16	Permit 2015-52, 15 Baynes Road. Went by late today to see wall forms. Only about one-half of the forms were up and only the outside wall form. I will have to go back sometime on Monday when he is ready.

Time 0.4

01-11-16	Permit 2015-52, 15 Baynes Road. Inspected the wall forms and they were okay.

Time 0.4

01-13-16	Permit 2015-52, 15 Baynes Road. Inspected the trench with sand, conduit installed from the transformer box almost to the foundation.

Time 0.4

01-20-16	Permit 2015-52, 15 Baynes Road. I inspected the perimeter drains except where the garage is going as they still need to get the site ready for the footer forms.

Time 0.3

01-22-16	Permit 2015-52, 15 Baynes Road. Inspected the footer forms for the attached garage. Rebar installed and supported, okay to pour.

Time 0.3

Time 0.9

01-26-16	Permit 2015-52, 15 Baynes Road. Inspected the frost wall forms for the attached garage. He installed three rows of rebar on the rear and left side walls. Okay.

Time .06

01-27-16	Permit 2015-52, 15 Baynes Road. Inspected the temporary electric service so the power utility would open up the transformer so the electrician could pull the cables from the transformer to the temporary circuit panel. The meter panel is supported against the foundation and is in its permanent location. Notified Liberty Utilities.

Time 0.5

03-08-16	Permit 2015-52, 15 Baynes Road. I went by to see the progress. The first floor was framed, the second floor as well although not all the flooring was installed. They were installing the roof rafters.

Time 0.5

04-04-16	Permit 2015-52, 15 Baynes Road. Needed to inspect the insulation and the radon plumbing so the could pour the basement floor. Looked okay.

Time 0.3

04-26-16	Permit 2015-52, 15 Baynes Road. I received a call to inspect the rough in plumbing. Most of the upstairs walls were wired and insulated. Most of the wiring was completed as well as the plumbing. Looked okay except that the penetrations needed to be fire stopped. Left a message for them as no one was on site.

Time 0.9

04-29-16	Permit 2015-52, 15 Baynes Road. Inspected the rest of the wiring and verified that penetrations were fire stopped. Okay to finish insulation and told them to call when ready.

Time 0.7

05-03-16	Permit 2015-52, 15 Baynes Road. Inspected the rest of the insulation and verified that penetrations were fire stopped.

Time 0.5

06-24-16	Permit 2015-52, 15 Baynes Road. Builder called to have me do an inspection for a Temporary Occupancy Certificate. Items needed to be completed prior to a CO: hand railing needs to be continuous, not in two sections; boiled needs relief valve plumbed to within four inches of floor; counter tops with sinks installed (temp. kitchen sink mounted in kitchen for TCO); insulation values posted on circuit panel; rear deck stairs completed. I will issue the temporary CO.

Time 0.7

07-05-16	Permit 2015-52, 15 Baynes Road. I went by to see if the discharge pipe was installed on the water heater, it was, and progress on the deck stairs, just some railing to be installed. Counter tops not there yet.

Time 0.4

07-27-16	Permit 2015-52, 15 Baynes Road. I went to do the final inspection. The deck stairs were completed, counter tops and sinks and appliances were installed in the kitchen and pantry, and the stair hand  railing was continuous.

Time 0.4

David H Lersch

Plainfield Building Inspector