DATE: 07/15/19

Permit Status (Valid for one year from issue date)

Permit # 2018-54  		Issued:  08-29-2018

_X__	RENEWAL REQUIRED BY __08___/__29__/__2019___

____	EXPIRED,  NO INSPECTION REQUESTED

__X_ 	LAST INSPECTION:		11-13-18

____ 	YOUR PERMIT REQUIRED INSPECTIONS PER  INSPECTION 				GUIDELINES (SEE INSPECTION GUIDELINES ATTACHED)

____	CLOSED  – YOUR PERMIT IS CLOSED, A NEW PERMIT IS REQUIRED

____	A CERTFICATE OF OCCUPANCY WAS REQUIRED PRIOR TO OCCUPYIING YOUR HOUSE

__X_	A CERTICICATE OF COMPLETION WAS  REQUIRED

NAME :     Guy Daniels

ADDRESS : 95 Beauty Hill Road

Plainfield, NH 03781

MAP/LOT: 	108-19				 ADDRESS:   42 Hayward Road

David H Lersch				     		603-381-1929

Plainfield Building Inspector

Guy Daniels

95 Beauty Hill Road

Plainfield

298-5373

Permit # 2018-54

Map/Lot 108/19

8x16 addition

42 Hayward Road

09-05-18	Permit 2018-54, 42 Hayward Road. Inspected the footer forms for the

addition with two rows of rebar supported on chairs. Gave okay to pour.

Time 0.4

09-10-18	Permit 2018-54, 42 Hayward Road. Inspected the wall forms for the addition with rebar installed, pinned to existing foundation wall.

Time 0.3

10-01-18	Permit 2018-42, 42 Hayward Road. Inspected the framing for the addition. Looked okay.

Time 0.3

11-06-18	Permit 2018-54, 42 Hayward Road. Received a text from contractor for a rough in electrical and plumbing inspection. Looked okay and they will insulate using fiberglass in the new 2x6 walls and foam where they had to remove existing foam in the 2x4 outside walls to do work.

Time 0.4

11-13-18	Permit 2018-54, 42 Hayward Road – Daniels – Friday 11/23 - 			inspection of insulation/air sealing in preparation for wall covering. 			Met contractor on-site. Air-sealing / insulation looked good. 				Questioned loose wire in closet. Contractor indicated that it would 			be removed. I indicated that if not removable should be run into 			accessible wall box. Not to be covered in wall. Otherwise ok to 			install wall covering.

BRAD

07-18-19	After sending letter, received a call to do the final inspection. 				Inspected okay, will issue a Certificate of Completion.

Time 0.3

David H Lersch

Plainfield Building Inspector