Jody C. Marsh

PO Box 698

Meriden

304-5051

Permit # 2016-57

Map/Lot 212/13

20x32 ranch, one bedroom, one bathroom, full basement

98 Methodist Hill Road

0-/26-16	Permit 2016-57, 98 Methodist Hill RoadI inspected the footer forms for 			the house. Ground wire was installed. Rebar supported by perpendicular 			rebar across the top of forms. He will fill forms half way drop rebar then 			finish filling. I usually require chairs or some other method to ensure the 			rebar is near the center for the footer and that will work.

Time 0.8

07-28-16	Permit 2016-57, 98 Methodist Hill Road. Inspected the foundation wall 			forms, rebar installed and tied together at corners. Okay to pour.

Time 0.5

08-02-16	Permit 2016-57, 98 Methodist Hill Road. Inspected the perimeter drains 			and trench down the hill to daylight.

Time 0.1

09-06-2016	Permit 2016-57, 98 Methodist Hill Road. Telephone call about stairs. 			Needs tread to be 10" or greater and no more than 7-3/4" rise.

Time 0.1

10-04-16	Permit 2016-57, 98 Methodist Hill Road. Inspected the framing, looked 			okay. Metal fire stop around chimney on first floor.

Time 0.2

10-20-16	Permit 2016-57, 98 Methodist Hill Road. Jody called and said all the 			framing was completed. Looked okay, chimney fire stop installed where it 		goes through first floor ceiling. Jody said the electrician should be starting 			soon.

Time 0.8

10-24-16 	Permit 2016-57, 98 Methodist Hill Road. Jody called to have me inspect 			the service entrance so they could get electrical service hooked up. 				Inspected the entrance and the circuit panel, also I inspected the rough in 			plumbing and electrical that was completed. I will notify Liberty Utilities.

Time 0.9

10-30-16 	Permit 2016-57, 98 Methodist Hill Road. Jody called yesterday and 			wanted me to inspect  the rough in electrical and plumbing. Looked okay 			except he needed to fire stop electrical and plumbing holes between floors. 		Will verify when the insulation inspection is done.

Time 1.0

11-19-16	Permit 2016-57, 98 Methodist Hill Road. Jody called and said he was 			ready for the insulation inspection. He had a professional install the 			insulation, The ceiling ended up at R49 and the walls at R20+. He sent my 		about 10 pictures to my cell phone, more than enough to see that 				everything was properly insulated. I gave the go to continue.

Time 0.3

Jody Marsh – 98 Methodist Hill Rd   New Home  Temp C.O.

Date: Dec. 6, 2016          Permit #:   2016-57       Activity: Inspect for temp c.o.

Met with owner on-site. Walls/Ceiling insulated w/ poly barrier on interior side of framing (no sheetrock). Electrical devices in w/o plates. Electric baseboard installed. Woodstove installed in single flue (no make-up air at this time) Smokes in/energized w/protective bags still on. Bath fixtures: w/c, tub/shower in and functioning. Lav on-site not installed. Fan in, ducted to outside. Kitchen: sink in and functioning. (temp set-up in new counter – no cabs) Range and fridge in. Entry (back) steps w/ 3 risers <30”. No handrail required. Front door to porch installed. Final grade at porch perimeter to be <30”, and completed in spring.

20 min. Brad

12-06-16	Permit 2016-57, 98 Methodist Hill Road. Jody sent pictures of bathroom, 			kitchen, smoke detectors, etc. Notified Brad to inspect for temporary CO. 			Michelle said Brad said it was okay and I printed the CO, signed, scanned, 		and emailed ninety day temporary CO.

11-15-17	Permit 2016-57, 98 Methodist Hill Road. Met with Jody to do the final 			inspection of his house. Dishwasher and microwave will be installed when 		they are eventually purchased. Electric baseboard heaters upstairs and 			wood stove downstairs. Bathroom and kitchen completed and operational. 			All landscaping completed. I will issue a Certificate of Occupancy.

Time 0.5

David H Lersch

Plainfield Building Inspector